## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: | 5 |  |  |  | Umer Qazi | uqazi2
Week Of: | 43577 |  |  |  | Farah Masood | mmasoo4
[5 empty] | Zaid Patel | zpatel24
[5 empty] | Mohammed Sami | msami4
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Set up GUI client server communication via serializable callback | p51 | Mohammed Sami | Allow Appropriate game play instructions to be displayed | Helped thread so that four players are able to connect
Set up 26 buttons on each client gui and disable | p52 | Farah Masood | Allow letter choice to be properly communicated to server and update word blanks | Created and sorted the hash map, and began trying the scoring process of the game
Regulate game play - keeping score, players turns, word being updated | p53 | Zaid Patel | Dictate player turns and updated word be reported to each client | Began to loop through the hash map in trying to pick a random word for the client, and trying to serialize the message
Allow threading (four clients to connect to one server) | p54 | Umer Qazi | after game is completed exit each client from server, and have 4 new clients connect to server for next game to begin | Implemented the done button in the game and created the set on action for the server gui